## Task Tracker
Task | Description | Status | Start Date | End Date
COMP1004 - Trivia Fiesta | Trivia Fiest is a browser-based Single Page Application (SPA) quiz system developed using vanilla HTML, CSS and JavaScript. | In Progress | 2025-10-07 | 2026-04-30
SPRINT 1 - Initiation | Project idea definition, project scope planning, and creation of the project initiation document outlining objectives, risks, and development approach. | Complete | 2025-10-07 | 2025-10-21
Define project idea and scope |  | Complete | 2025-10-07 | 2025-10-21
Identify functional and non-functional requirements |  | Complete | 2025-10-07 | 2025-10-21
Plan development approach using Scrum and Waterfall |  | Complete | 2025-10-07 | 2025-10-21
Write project initiation document |  | Complete | 2025-10-07 | 2025-10-21
SPRINT 2 - Requirements & Planning | Definition of quiz features, creation of the JSON structure for quiz data, collection of bilingual question examples, and initial planning of the user interface. | Complete | 2025-10-22 | 2025-11-04
Define quiz features (categories, scoring, bilingual support) |  | Complete | 2025-10-22 | 2025-11-04
Design JSON structure for quiz data |  | Complete | 2025-10-22 | 2025-11-04
Gather example questions in English and Greek |  | Complete | 2025-10-22 | 2025-11-04
Plan UI layout |  | Complete | 2025-10-22 | 2025-11-04
SPRINT 3 - Initial Implementation | Creation of the project repository and initial application structure, including HTML layout, SPA container setup, helper functions, and project documentation. | Complete | 2025-11-05 | 2025-11-19
Set up project repository |  | Complete | 2025-11-05 | 2025-11-19
Build HTML layout |  | Complete | 2025-11-05 | 2025-11-19
Implement SPA containers |  | Complete | 2025-11-05 | 2025-11-19
Add helper function |  | Complete | 2025-11-05 | 2025-11-19
Write READ.ME |  | Complete | 2025-11-05 | 2025-11-19
SPRINT 4 - Core Quiz Functionality | Implementation of the main quiz logic including category selection, question rendering, answer validation, and score tracking. | Complete | 2025-11-20 | 2025-12-11
Category selection system |  | Complete | 2025-11-20 | 2025-12-11
Question rendering |  | Complete | 2025-11-20 | 2025-12-11
Answer selection logic |  | Complete | 2025-11-20 | 2025-12-11
Score tracking |  | Complete | 2025-11-20 | 2025-12-11
SPRINT 5 - Mid Project Submission | Preparation of mid-project deliverables including the personal development paragraph, presentation, and submission of the mid-project video demonstration. | Complete | 2025-12-12 | 2026-01-09
Personal development paragraph |  | Complete | 2025-12-12 | 2025-12-19
Powerpoint |  | Complete | 2025-12-12 | 2025-12-19
Christmas Break |  | Complete | 2025-12-20 | 2026-01-03
Mid project video submission |  | Complete | 2026-01-04 | 2026-01-09
SPRINT 6 - Advanced Features | Development of additional interactive features including the countdown timer, sound effects, theme toggle (light/dark mode), and difficulty filtering. | Complete | 2026-01-10 | 2026-01-31
Timer system |  | Complete | 2026-01-10 | 2026-01-31
Sound effects |  | Complete | 2026-01-10 | 2026-01-31
Light / Dark mode |  | Complete | 2026-01-10 | 2026-01-31
Difficulty filtering |  | Complete | 2026-01-10 | 2026-01-31
SPRINT 7 - Custom Quiz Feature | Implementation of custom quiz functionality allowing users to download a JSON template and upload their own quizzes with validation checks. | Complete | 2026-02-01 | 2026-02-15
JSON template download |  | Complete | 2026-02-01 | 2026-02-15
Custom quiz upload |  | Complete | 2026-02-01 | 2026-02-15
Error messages |  | Complete | 2026-02-01 | 2026-02-15
JSON structure validation |  | Complete | 2026-02-01 | 2026-02-15
SPRINT 8 - Testing & Refinement | System testing and interface improvements including bug fixes, UI adjustments, validation testing, leaderboard functionality, and navigation corrections. | Complete | 2026-02-16 | 2026-03-02
Bug fixes |  | Complete | 2026-02-16 | 2026-03-02
UI improvements |  | Complete | 2026-02-16 | 2026-03-02
Validation testing |  | Complete | 2026-02-16 | 2026-03-02
Leaderboard functionality |  | Complete | 2026-02-16 | 2026-03-02
Navigation fixes (back button / timer reset) |  | Complete | 2026-02-16 | 2026-03-02
SPRINT 9 - Finalisation | Final project refinement including JSON score export, code commenting, poster creation, report writing, final testing, and submission preparation. | Complete | 2026-03-03 | 2026-04-30
JSON score export |  | Complete | 2026-03-03 | 2026-03-17
Final code comments |  | Complete | 2026-03-03 | 2026-03-17
Final UI polishing |  | Complete | 2026-03-03 | 2026-03-17
Create poster |  | Complete | 2026-03-18 | 2026-03-29
Write report |  | Complete | 2026-03-18 | 2026-03-29
Final application test |  | Complete | 2026-03-18 | 2026-03-29
Spring/Easter break |  | Complete | 2026-03-30 | 2026-04-17
Submission checklist |  | Complete | 2026-04-18 | 2026-04-30